| Project | Project Manager | Date |
| --- | --- | --- |
| Doon: Smart Regional Activity Tracking and Recommendation System | Asst. Prof. Benjie R. Samonte | March 12, 2026 |

Justification

Tourism data across the five provinces of CALABARZON (Batangas, Laguna, Cavite, Rizal, and Quezon) is scattered across social media, travel blogs, and informal channels with no single, reliable source for Tourists, Local service providers, or Local Government Units (LGUs). This fragmentation makes trip planning inefficient and reduces regional tourism potential. The Doon project addresses this by developing an AI-powered web and mobile platform that integrates data from community organizations, service providers, tourism offices, and LGUs into a single, unified regional hub. It delivers personalized activity recommendations based on user preferences, budget, travel time, and generational profile; real-time travel assistance; an interactive regional map; an AI chatbot for travel guidance; and smart travel features including automated itinerary planning, weather integration, and packing suggestions. The project also aligns with UN Sustainable Development Goals SDG 8 (Decent Work and Economic Growth), SDG 9 (Industry, Innovation and Infrastructure), SDG 11 (Sustainable Cities and Communities), and SDG 12 (Responsible Consumption and Production).

| In-Scope Functionality | Priority (MoSCoW) |
| --- | --- |
| RECOMMENDATION ENGINE & CORE PLATFORM |  |
| AI-powered multi-criteria recommendation engine (budget, theme, number of people, trip duration, generational profile) | M — Must |
| AI Chatbot for interactive travel guidance and destination suggestions | M — Must |
| Web-based and mobile-responsive Doon platform for the CALABARZON region | M — Must |
| Three user roles: Tourist, Local (service providers and municipalities), Admin | M — Must |
| DISCOVERY & MAPPING |  |
| Interactive Regional Map integrated with third-party geolocation and mapping APIs | M — Must |
| Regional Activity and Destination Database covering events, attractions, accommodations, food, and transit across all five CALABARZON provinces | M — Must |
| Local Business and Activity Directory for service providers, accommodations, restaurants, and event organizers | S — Should |
| User Reviews and Ratings system for continuous quality improvement | S — Should |
| SMART TRAVEL FEATURES |  |
| Automated itinerary planning based on user preferences and travel parameters | M — Must |
| Real-time weather integration with forecasting and travel advisories | M — Must |
| "What to Bring" packing suggestions and wardrobe recommendations based on activity and destination | S — Should |
| GOVERNMENT & ANALYTICS |  |
| LGU and Stakeholder Analytics Dashboard with automated monthly reports on visitor behavior and destination performance | S — Should |
| Activity Provider Portal for local businesses and event coordinators to submit and manage listings | S — Should |
| SYSTEM & PROJECT DOCUMENTATION |  |
| Third-party API integrations (geolocation/maps and weather) | M — Must |
| UI/UX design, prototypes, and wireframes for all three user roles | M — Must |
| System testing: functional, integration, performance, and security | M — Must |
| Full project documentation per the WBS (all 18 deliverables) | M — Must |
| Formal customer acceptance and project closeout | M — Must |

| Out-of-Scope Functionality | Priority (MoSCoW) |
| --- | --- |
| Standalone native mobile application (iOS/Android) — deferred to future phase | W — Won't |
| SMS gateway integration for notifications — deferred to future phase | W — Won't |
| Payment gateway or e-commerce transaction processing for bookings — deferred to future phase | W — Won't |
| Direct integration with national government information systems (DICT, DOT national databases) | W — Won't |
| AI-powered medical, safety, or emergency response capabilities | W — Won't |
| Electronic travel document, passport, or visa processing | W — Won't |
| Offline functionality for areas without internet connectivity | C — Could |
| Expansion beyond the five CALABARZON provinces in the current phase | C — Could |
| Hardware procurement for LGU offices | W — Won't |
| End-user onboarding and training programs beyond system handover | S — Should |

| Business Objective | Description |
| --- | --- |
| Deliver All Deliverables on Schedule | Submit all 18 project deliverables on or before their Gantt Chart due dates; project closes by May 15, 2026. |
| Obtain Project Charter Sign-Off | Secure formal authorization of the Doon project through a signed Project Charter approved by Asst. Prof. Arlene M. Mendoza. |
| Complete Planning Phase by March 12 | Produce all five Planning deliverables (Gantt Chart, WBS, Project Scope Document, Project Requirements Document, Project Management Plan) by March 12, 2026. |
| Complete Execution Deliverables | Produce Prototypes and Wireframes, Test Plan, Test Cases, and Test Report by May 7, 2026 with no critical defects outstanding. |
| Obtain Customer Acceptance Form | Secure formal sign-off from the Project Sponsor confirming the Doon platform meets all agreed requirements by May 15, 2026. |
| Align with SDG Goals | Demonstrate measurable alignment with SDG 8 (Decent Work and Economic Growth), SDG 9 (Industry, Innovation and Infrastructure), SDG 11 (Sustainable Cities and Communities), and SDG 12 (Responsible Consumption and Production). |

| WBS Code | Deliverable | Description |
| --- | --- | --- |
| Phase 1 | INITIATION |  |
| 1.1.1 | Letter to Sponsor | Formal written request to the project sponsor seeking approval and institutional support for the Doon project. |
| 1.1.2 | Project Staffing Profile | Document outlining team roles, responsibilities, and assigned competencies for each of the five team members. |
| 1.1.3 | Business Case | Justification document presenting the problem, expected benefits, estimated costs, risks, and strategic rationale for the Doon project. |
| 1.1.4 | Preliminary Investigation Report | Feasibility assessment covering technical, organizational, and financial viability of the Doon platform. |
| 1.1.5 | Kick Off Meeting | Formal meeting conducted February 26, 2026 to officially launch the project, confirm team roles, and align on scope and schedule. |
| 1.1.6 | Project Charter | Formal document authorizing the Doon project, signed by Asst. Prof. Arlene M. Mendoza as Project Sponsor. |
| Phase 2 | PLANNING |  |
| 1.2.1 | Gantt Chart | Visual project schedule showing all 18 deliverables, durations, start/finish dates, and predecessor relationships. |
| 1.2.2 | WBS | Hierarchical decomposition of all project work across five phases into Level 3 work packages. |
| 1.2.3 | Project Scope Document | This document. Defines project boundaries, in-scope/out-of-scope features, deliverables, constraints, and cost estimates. |
| 1.2.4 | Project Requirements Document | Functional and non-functional requirements for the Doon platform covering all three user roles. |
| 1.2.5 | Project Management Plan | Integrated planning document consolidating schedule baseline, risk register, communication plan, and resource allocation. |
| Phase 3 | EXECUTION |  |
| 1.3.1 | Prototypes and Wireframes | UI/UX wireframes and interactive prototypes for Tourist, Local, and Admin roles designed in Figma. |
| 1.3.2 | Test Plan | Document defining the testing strategy, scope, schedule, environment, and responsibilities for the Doon system. |
| 1.3.3 | Test Cases | Specific test scenarios, inputs, and expected outcomes for all functional and non-functional requirements. |
| 1.3.4 | Test Report | Summary of test execution results, defects found, resolution status, and overall quality assessment. |
| Phase 4 | CONTROL (Concurrent) |  |
| 1.4.1 | Milestone Report | Progress report summarizing accomplishments, schedule adherence, current risks, and next steps at key control points. |
| Phase 5 | CLOSEOUT |  |
| 1.5.1 | Lessons Learned Report | Documentation of project successes, challenges, and improvement recommendations for future BSU ARASOF-Nasugbu projects. |
| 1.5.2 | Customer Acceptance Form | Formal sign-off document confirming all Doon deliverables and system functionality accepted by the Project Sponsor. |

Project Exclusions

The following items are explicitly outside the scope of the Doon project. These may be addressed in future phases or separate initiatives: - Standalone native mobile application (iOS/Android) — the platform is web-based and mobile-responsive only; a native app is identified as a future enhancement. - SMS gateway integration for push notifications — deferred to a future phase due to licensing cost and complexity. - Payment gateway or e-commerce transaction processing for tour bookings — deferred to future phase. - Direct integration with national government databases (DICT, DOT national systems, PSA) — out of scope for this version. - AI-powered medical, safety, or emergency response capabilities — the system is a tourism and activity recommendation platform only. - Expansion beyond the five CALABARZON provinces (Batangas, Laguna, Cavite, Rizal, Quezon) — future phases may cover additional regions. - Hardware procurement for LGU offices or partner institutions. - End-user onboarding and training programs beyond system handover and basic documentation. - Offline functionality for areas without internet connectivity.

| Constraint Type | Constraint | Impact |
| --- | --- | --- |
| Time | Project must close by May 15, 2026 | All 18 deliverables have fixed due dates per the Gantt Chart; delays cascade through predecessor-linked tasks. |
| Budget | Must be delivered within institutional academic budget | Platform built on open-source technologies (Laravel, React, Flutter, PostgreSQL, GitHub); estimated external costs limited to cloud hosting, domain, and API keys. |
| Technology | Confirmed tech stack must be used throughout | Platform must use Laravel, React, Flutter, PostgreSQL, and Figma as confirmed at Kick Off; deviations require Sponsor approval. |
| Scope | No scope changes after Kick Off Meeting (Feb 26, 2026) | Any scope change after February 26, 2026 requires formal review and written approval from Asst. Prof. Arlene M. Mendoza. |
| Resources | Fixed five-member team | Team is fixed at Adona, Bebita, Eleponga, Pagkaliwagan, and Villaflor; unavailability of any member delays dependent deliverables. |
| Data Privacy | Data Privacy Act of 2012 compliance required | Collection and use of user location and behavioral data requires explicit user consent; role-based access and secure authentication must be implemented. |
| Third-Party APIs | API availability and pricing may limit scope | Geolocation and weather API availability, rate limits, and licensing costs may constrain real-time features; fallback plans required. |

| No. | Assumption | Rationale |
| --- | --- | --- |
| 1 | All five team members remain available for the full project duration (Feb 12 – May 15, 2026) | All roles are assigned to specific individuals; no backup personnel are identified. Absence of any member will delay deliverables on the critical path. |
| 2 | Regional activity data from LGUs will be made available to the team | The Doon recommendation engine and destination database depend on tourism data provided by LGU partners across the five CALABARZON provinces. |
| 3 | Project Sponsor will review and approve deliverables within agreed timelines | Asst. Prof. Arlene M. Mendoza is expected to provide timely feedback and sign-offs; delays in approvals will affect the project schedule. |
| 4 | Required tools remain accessible throughout the project | Laravel, React, Flutter, PostgreSQL, Figma, GitHub, and third-party geolocation and weather APIs are assumed to remain freely or affordably accessible for the full project duration. |
| 5 | No major scope changes will be approved after the Kick Off Meeting | Scope was formally confirmed at the Kick Off Meeting on February 26, 2026. Any approved change after this date will require schedule and cost re-evaluation. |
| 6 | End users will consent to location-based tracking and activity preference collection | Compliance with the Data Privacy Act of 2012 requires explicit user consent; the recommendation engine cannot function without access to location and preference data. |
| 7 | Cloud infrastructure will be procured and configured before Execution phase begins | Development and testing environments must be available before Prototypes and Wireframes work begins on March 18, 2026. |
| 8 | LGU partners and key stakeholders will be available for review and feedback | Stakeholder validation is required for UI/UX prototypes and final UAT; their availability is assumed throughout the Execution phase. |

| Item / Resource | Estimated Cost | Actual Cost | Cost Until Completion | Variance |
| --- | --- | --- | --- | --- |
| Software Licenses (Laravel, React, Flutter, PostgreSQL, GitHub — Open Source) | ₱0 | ₱0 | ₱0 | ₱0 |
| Figma — UI/UX Design Tool (Free Tier) | ₱0 | ₱0 | ₱0 | ₱0 |
| OpenWeatherMap API (Free Tier) | ₱0 | ₱0 | ₱0 | ₱0 |
| SSL Certificate (Let's Encrypt — Free) | ₱0 | ₱0 | ₱0 | ₱0 |
| Google Maps / Geolocation API (3-month estimate) | ₱1,500 | ₱0 | ₱1,500 | ₱0 |
| Cloud Hosting — DigitalOcean or equivalent (3 months) | ₱3,500 | ₱0 | ₱3,500 | ₱0 |
| Domain Name Registration (1 year) | ₱800 | ₱0 | ₱800 | ₱0 |
| Printing & Documentation (reports, sign-off forms) | ₱500 | ₱0 | ₱500 | ₱0 |
| Miscellaneous & Contingency (10%) | ₱630 | ₱0 | ₱630 | ₱0 |
| TOTAL | ₱6,930 | ₱0 | ₱6,930 | ₱0 |