# Work Breakdown Structure

Doon: Smart Regional Activity Tracking and Recommendation System

Batangas State University ARASOF — Nasugbu, TNEU

R. Martinez St., Brgy. Bucana,

Nasugbu, Batangas, 4231

AUTHOR/S

Adona, Linux S.

Bebita, Jessa Marie E.

Eleponga, Felman I.

Pagkaliwagan, Zeth Ramzy A.

Villaflor, Djanisse N.

March 7, 2026

TABLE OF CONTENTS

Introduction	1

Outline View	1

Hierarchical Structure	2

Tabular View	2

Tree Structure View	3

WBS Dictionary	3

Glossary of Terms	5

REFERENCES	8

AUTHORSHIP	10

AUTHORIZATION	10

# Introduction

This Work Breakdown Structure (WBS) documents all the work required to design, develop, deploy, and close out the Doon: Smart Regional Activity Tracking and Recommendation System — an AI-powered web and mobile platform developed for the CALABARZON region.

The fragmented status of tourism information in the five provinces of CALABARZON (Batangas, Laguna, Cavite, Rizal, and Quezon) inspired the creation of the Doon project. There is currently no centralized platform that links visitors, local companies, and Local Government Units (LGUs. In order to address this, Doon offers regional stakeholders' data-driven insights, real-time travel assistance, integrated trip planning, and personalized activity recommendations, all on a single, unified platform.

This work breakdown structure (WBS) will be used by the project manager and team to create the project schedule, allocate resources, and calculate expenses for each of the five project phases—initiation, planning, execution, control, and closeout. It is crucial to remember that Control operates simultaneously across the whole project lifecycle, from Initiation to Closeout, and is not a sequential phase.

To meet the demands of various stakeholders, this document present the WBS in a variety of formats, including Outline View, Hierarchical Structure, Tabular View, Tree Structure View, and WBS Dictionary. At present, the WBS is divided into Level 3. The 8 to 80 rule, which states that each work package has between 8 and 80 hours of work to complete, should be used in practice to further break down jobs.

# Outline View

The Outline View below presents the complete hierarchical breakdown of all work required to deliver the Doon system. It is organized across five phases, the Initiation, Planning, Execution, Control, and Closeout and broken down into Level 3 work packages. Each deliverable in this view corresponds directly to a task tracked in the project Gantt Chart

Doon: Smart Regional Activity Tracking and Recommendation System

1.1  Initiation

    - Deliverable: Letter to Sponsor

    - Deliverable: Project Staffing Profile

    - Deliverable: Business Case

    - Deliverable: Preliminary Investigation Report

    - Kick Off Meeting

    - Deliverable: Project Charter

1.2  Planning

    - Deliverable: Gantt Chart

    - Deliverable: WBS

    - Deliverable: Project Scope Document

    - Deliverable: Project Requirements Document

    - Deliverable: Project Management Plan

1.3  Execution

    - Deliverable: Prototypes and Wireframes

    - Deliverable: Test Plan

    - Deliverable: Test Cases

    - Deliverable: Test Report

1.4  Control

    - Deliverable: Milestone Report

1.5  Closeout

    - Deliverable: Lessons Learned Report

    - Deliverable: Customer Acceptance Form

# Hierarchical Structure

| Level | WBS Code | Element Name |
| --- | --- | --- |
| 1 | 1 | Doon: Smart Regional Activity Tracking and Recommendation System |
| 2 | 1.1 | Initiation |
| 3 | 1.1.1 | Deliverable: Letter to Sponsor |
| 3 | 1.1.2 | Deliverable: Project Staffing Profile |
| 3 | 1.1.3 | Deliverable: Business Case |
| 3 | 1.1.4 | Deliverable: Preliminary Investigation Report |
| 3 | 1.1.5 | Kick Off Meeting |
| 3 | 1.1.6 | Deliverable: Project Charter |
| 2 | 1.2 | Planning |
| 3 | 1.2.1 | Deliverable: Gantt Chart |
| 3 | 1.2.2 | Deliverable: WBS |
| 3 | 1.2.3 | Deliverable: Project Scope Document |
| 3 | 1.2.4 | Deliverable: Project Requirements Document |
| 3 | 1.2.5 | Deliverable: Project Management Plan |
| 2 | 1.3 | Execution |
| 3 | 1.3.1 | Deliverable: Prototypes and Wireframes |
| 3 | 1.3.2 | Deliverable: Test Plan |
| 3 | 1.3.3 | Deliverable: Test Cases |
| 3 | 1.3.4 | Deliverable: Test Report |
| 2 | 1.4 | Control |
| 3 | 1.4.1 | Deliverable: Milestone Report |
| 2 | 1.5 | Closeout |
| 3 | 1.5.1 | Deliverable: Lessons Learned Report |
| 3 | 1.5.2 | Deliverable: Customer Acceptance Form |

# Tabular View

| Level 1 | Level 2 | Level 3 |
| --- | --- | --- |
| 1 Doon Platform | 1.1 Initiation | 1.1.1 Deliverable: Letter to Sponsor 1.1.2 Deliverable: Project Staffing Profile 1.1.3 Deliverable: Business Case 1.1.4 Deliverable: Preliminary Investigation Report 1.1.5 Kick Off Meeting 1.1.6 Deliverable: Project Charter |
|  | 1.2 Planning | 1.2.1 Deliverable: Gantt Chart 1.2.2 Deliverable: WBS 1.2.3 Deliverable: Project Scope Document 1.2.4 Deliverable: Project Requirements Document 1.2.5 Deliverable: Project Management Plan |
|  | 1.3 Execution | 1.3.1 Deliverable: Prototypes and Wireframes 1.3.2 Deliverable: Test Plan 1.3.3 Deliverable: Test Cases 1.3.4 Deliverable: Test Report |
|  | 1.4 Control | 1.4.1 Deliverable: Milestone Report |
|  | 1.5 Closeout | 1.5.1 Deliverable: Lessons Learned Report 1.5.2 Deliverable: Customer Acceptance Form |

# Tree Structure View

The Tree Structure View is the most commonly used format for presenting a Work Breakdown Structure. It displays the hierarchical decomposition of the Doon project in an organisational-chart layout, with the root project element at the top and the five project phases branching downward. Each phase further expands into its respective Level 3 work packages. This format provides an intuitive, at-a-glance understanding of the entire scope of work and the relationships between deliverables.

# WBS Dictionary

The WBS Dictionary contains all the details of the WBS which are necessary to successfully complete the project. Most importantly it contains a definition of each Work Package which can be thought of as a mini-scope statement. Resources on the project will look at the WBS dictionary to determine the scope of the Work Package they have been assigned.

| Level | WBS | Element Name | Definition |
| --- | --- | --- | --- |
| 1 | 1 | Doon: Smart Regional Activity Tracking and Recommendation System | All work required to design, develop, deploy, and close the AI-powered regional tourism platform for CALABARZON. |
| 2 | 1.1 | Initiation | Work required to formally authorize and start the project. |
| 3 | 1.1.1 | Deliverable: Letter to Sponsor | A formal letter requesting project approval and support from the designated project sponsor. |
| 3 | 1.1.2 | Deliverable: Project Staffing Profile | A document outlining the project team roles, required skills, and staffing assignments. |
| 3 | 1.1.3 | Deliverable: Business Case | A document justifying the project by outlining benefits, costs, risks, and strategic alignment with goals. |
| 3 | 1.1.4 | Deliverable: Preliminary Investigation Report | A report assessing the project&#x2019;s feasibility and recommending whether to proceed. |
| 3 | 1.1.5 | Kick Off Meeting | A formal meeting held with the project sponsor and stakeholders to officially authorize and launch the project. |
| 3 | 1.1.6 | Deliverable: Project Charter | The formal document defining project objectives, scope, stakeholders, and project manager authority. Signed by the sponsor. |
| 2 | 1.2 | Planning | Activities required to define the detailed project scope, schedule, resources, and cost estimates. |
| 3 | 1.2.1 | Deliverable: Gantt Chart | A timeline chart showing all project deliverables, their durations, start/finish dates, and predecessor relationships. |
| 3 | 1.2.2 | Deliverable: WBS | The Work Breakdown Structure document decomposing the project into phases, work packages, and deliverables. |
| 3 | 1.2.3 | Deliverable: Project Scope Document | A document defining the project&#x2019;s objectives, deliverables, boundaries, constraints, and key requirements. |
| 3 | 1.2.4 | Deliverable: Project Requirements Document | A document detailing the functional and non-functional requirements the Doon system must meet. |
| 3 | 1.2.5 | Deliverable: Project Management Plan | The integrated plan consolidating the schedule, cost baseline, risk register, quality plan, and communication plan. |
| 2 | 1.3 | Execution | Activities required to build, integrate, test, and deploy the Doon system. |
| 3 | 1.3.1 | Deliverable: Prototypes and Wireframes | Visual drafts and interactive mockups showing the design and layout of the system for all three user roles before full development. |
| 3 | 1.3.2 | Deliverable: Test Plan | A document outlining how the system will be tested, including test methods, scope, environment, and expected outcomes. |
| 3 | 1.3.3 | Deliverable: Test Cases | Specific scenarios used to verify that the Doon platform functions correctly against defined requirements. |
| 3 | 1.3.4 | Deliverable: Test Report | A document summarizing test execution results, defects found, resolution status, and overall system quality assessment. |
| 2 | 1.4 | Control | Continuous monitoring and management activities running concurrently across all project phases. |
| 3 | 1.4.1 | Deliverable: Milestone Report | A progress report prepared at key project stages summarizing achievements, status against plan, risks, and next steps. |
| 2 | 1.5 | Closeout | Formal activities required to complete and officially close the project. |
| 3 | 1.5.1 | Deliverable: Lessons Learned Report | A document recording project successes, challenges, and improvement recommendations for future projects. |
| 3 | 1.5.2 | Deliverable: Customer Acceptance Form | The formal sign-off document obtained from the project sponsor and stakeholders confirming system acceptance. |

# Glossary of Terms

The following glossary defines key terms used throughout this Work Breakdown Structure document. It is intended to ensure a common understanding among all project stakeholders — including team members, sponsors, and LGU partners — regardless of their project management background. Terms are listed alphabetically and include both standard project management vocabulary as defined by the PMI Practice Standard for Work Breakdown Structures and Doon-specific terminology relevant to the CALABARZON regional tourism platform.

| Term | Definition |
| --- | --- |
| AI Recommendation Engine | An artificial intelligence module within the Doon platform that analyses user-supplied parameters — budget, generational profile, trip duration, number of travellers, and activity theme — to produce personalised activity and destination suggestions using multi-criteria decision-making. |
| Business Case | WBS deliverable 1.1.3. A document justifying the Doon project by outlining expected benefits, estimated costs, identified risks, and strategic alignment with regional tourism development goals. It provides the basis for sponsor approval to proceed. |
| CALABARZON | The administrative region in the Philippines comprising the five provinces of Cavite, Laguna, Batangas, Rizal, and Quezon. CALABARZON is the primary geographic scope of the Doon platform. |
| Closeout | WBS phase 1.5. The final phase in which all project activities are formally concluded, including delivery of the Lessons Learned Report and obtaining the Customer Acceptance Form from the project sponsor. |
| Control | WBS phase 1.4. A cross-cutting phase that runs concurrently with all other phases, encompassing project monitoring, status reporting, and production of the Milestone Report (1.4.1). |
| Customer Acceptance Form | WBS deliverable 1.5.2. The formal sign-off document obtained from the project sponsor and stakeholders confirming that the Doon system meets all agreed requirements and is accepted for production use. |
| Deliverable | A tangible or verifiable output produced as part of a work package. In this WBS, deliverables include the Project Charter, Gantt Chart, Prototypes and Wireframes, Test Report, and Customer Acceptance Form, among others. |
| Execution | WBS phase 1.3. Covers all activities required to build and verify the Doon system, including Prototypes and Wireframes (1.3.1), Test Plan (1.3.2), Test Cases (1.3.3), and Test Report (1.3.4). |
| Gantt Chart | WBS deliverable 1.2.1. A timeline chart showing all project deliverables, their durations, start and finish dates, and predecessor relationships. Serves as the primary schedule management tool for the Doon project. |
| Initiation | WBS phase 1.1. Covers the activities required to formally recognise and authorise the Doon project, from the Letter to Sponsor (1.1.1) through to the signed Project Charter (1.1.6). |
| Kick Off Meeting | WBS work package 1.1.5. A formal meeting conducted with the project sponsor and key stakeholders to officially launch the Doon project, confirm roles and responsibilities, and align on project objectives and schedule. |
| Lessons Learned Report | WBS deliverable 1.5.1. A document recording project successes, challenges, process deviations, and improvement recommendations for future projects of similar scope within Batangas State University. |
| Letter to Sponsor | WBS deliverable 1.1.1. A formal written request addressed to the designated project sponsor seeking approval and institutional support for the Doon project, including a brief project overview and resource commitments required. |
| Level of Effort (LOE) | The quantity of work — expressed in person-hours — required to complete a specific work package. The 8-to-80 rule, as recommended in the PMI Practice Standard for Work Breakdown Structures, states that each work package should represent between 8 and 80 hours of effort. |
| LGU (Local Government Unit) | A provincial or municipal government body within the CALABARZON region. LGUs are key data providers and stakeholders of the Doon platform, particularly for tourism destination listings and local activity information. |
| Milestone | A scheduled point in the project timeline signifying the completion of a major deliverable or phase gate. Milestones carry zero duration. In this WBS, the Milestone Report (1.4.1) formally captures achievement status at key control points. |
| Milestone Report | WBS deliverable 1.4.1. A progress report prepared at key project stages that summarises accomplishments, compares actual versus planned progress, identifies current risks, and outlines next steps for the Doon project. |
| Planning | WBS phase 1.2. Covers all activities required to define the detailed project scope, schedule, and resource plan, from the Gantt Chart (1.2.1) and WBS (1.2.2) through to the Project Management Plan (1.2.5). |
| Preliminary Investigation Report | WBS deliverable 1.1.4. A report assessing the Doon project's technical and organisational feasibility, identifying potential constraints and risks, and providing a recommendation on whether to proceed to full planning. |
| Project Charter | WBS deliverable 1.1.6. The formal document that authorises the existence of the Doon project, defines high-level objectives and scope boundaries, identifies key stakeholders, and establishes the project manager's authority. |
| Project Management Plan | WBS deliverable 1.2.5. The integrated planning document that consolidates the schedule baseline, cost estimates, risk register, quality plan, communication plan, and resource allocation for the Doon project. |
| Project Requirements Document | WBS deliverable 1.2.4. A document detailing the functional and non-functional requirements the Doon system must satisfy, including user role specifications, system performance criteria, and integration requirements. |
| Project Scope Document | WBS deliverable 1.2.3. A document defining the Doon project's objectives, in-scope and out-of-scope boundaries, key deliverables, constraints, and assumptions agreed upon with the project sponsor. |
| Project Staffing Profile | WBS deliverable 1.1.2. A document outlining the roles required for the Doon project team, specifying responsibilities, required competencies, and staffing assignments for each team member. |
| Prototypes and Wireframes | WBS deliverable 1.3.1. Visual drafts and interactive mockups representing the design and layout of the Doon system for all user roles — Tourist, Local Service Provider, and LGU Admin — produced using Figma and validated with stakeholders prior to development. |
| Test Cases | WBS deliverable 1.3.3. Specific test scenarios, inputs, and expected outcomes used to verify that the Doon platform functions correctly against each defined functional and non-functional requirement. |
| Test Plan | WBS deliverable 1.3.2. A document outlining the strategy, scope, schedule, environment, tools, and responsibilities for testing the Doon system, covering unit, integration, and system test activities. |
| Test Report | WBS deliverable 1.3.4. A document summarising the results of all test executions, including defects discovered, their resolution status, re-test outcomes, and an overall assessment of system quality and readiness. |
| Tree Structure View | A hierarchical diagram presenting the WBS decomposition in an organisational-chart format, with the project root at the top and successive levels branching downward. It provides an intuitive visual overview of the complete work breakdown. |
| WBS (Work Breakdown Structure Document) | WBS deliverable 1.2.2. The formal document decomposing the total project scope into phases and work packages. It includes the Outline View, Hierarchical Structure, Tabular View, Tree Structure View, and WBS Dictionary. |
| WBS Code | A unique numeric identifier assigned to every element in the Work Breakdown Structure, reflecting its hierarchical position. For example, 1.2.3 identifies the third work package within the Planning phase (1.2) of the Doon project (1). |
| WBS Component | Any element within the WBS — whether a summary element, a WBS element, or a work package. The term encompasses items at all levels of the hierarchy. |
| WBS Dictionary | A companion document to the WBS that provides a concise definition, scope description, and contextual information for each element. It serves as a mini scope statement for every assignable unit of work in the Doon project. |
| WBS Element | A single node within the WBS, together with its associated attributes. A WBS element may summarise child elements or represent a work package; it exists at any level of the hierarchy. |
| Work Breakdown Structure (WBS) | A hierarchical decomposition of the total scope of work required to accomplish the Doon project objectives and create the specified deliverables. Each descending level represents an increasingly detailed definition of project work, as defined in the PMI Practice Standard for Work Breakdown Structures. |
| Work Package | The lowest-level element in a WBS branch. A work package is a discrete, assignable unit of work with a defined deliverable, an identifiable owner, and an estimable duration and cost. In this WBS, all Level 3 elements constitute work packages. |

# REFERENCES

[1] Project Management Institute, A Guide to the Project Management Body of Knowledge (PMBOK&reg; Guide), 7th ed. Newtown Square, PA, USA: Project Management Institute, 2021.

[2] Project Management Institute, Practice Standard for Work Breakdown Structures, 3rd ed. Newtown Square, PA, USA: Project Management Institute, 2019.

[3] Project Management Institute, Practice Standard for Scheduling, 2nd ed. Newtown Square, PA, USA: Project Management Institute, 2011.

[4] B. Mulcahy, Project Management Professional (PMP)&reg; Exam Prep, 10th ed. RMC Publications, Inc., 2020.

[5] H. Kerzner, Project Management: A Systems Approach to Planning, Scheduling, and Controlling, 13th ed. Hoboken, NJ, USA: John Wiley & Sons, 2022.

[6] Department of Information and Communications Technology (DICT), "National ICT Ecosystem Framework (NICTEF)," Republic of the Philippines, Quezon City, Philippines, 2017.

[7] Department of Tourism (DOT), "Philippine Tourism Statistics 2023," Republic of the Philippines, Manila, Philippines, 2023.

[8] National Economic and Development Authority (NEDA), "Regional Development Plan 2023-2028: CALABARZON," Republic of the Philippines, Pasig City, Philippines, 2023.

[9] Laravel LLC, "Laravel 11.x Documentation," 2024. [Online]. Available: https://laravel.com/docs. [Accessed: Mar. 2025].

[10] Meta Platforms, Inc., "React Documentation," 2024. [Online]. Available: https://react.dev. [Accessed: Mar. 2025].

[11] Google LLC, "Flutter Documentation," 2024. [Online]. Available: https://flutter.dev/docs. [Accessed: Mar. 2025].

[12] PostgreSQL Global Development Group, "PostgreSQL 16 Documentation," 2024. [Online]. Available: https://www.postgresql.org/docs/16/. [Accessed: Mar. 2025].

[13] Figma, Inc., "Figma Design Tool Documentation," 2024. [Online]. Available: https://help.figma.com. [Accessed: Mar. 2025].

[14] Institute of Electrical and Electronics Engineers, "IEEE Standard for Software and System Test Documentation," IEEE Std 829-2008, New York, NY, USA: IEEE, 2008.

[15] Commission on Higher Education (CHED), "CHED Memorandum Order No. 20, Series of 2023: Revised Policies, Standards and Guidelines for the Bachelor of Science in Information Technology," Republic of the Philippines, Quezon City, Philippines, 2023.

# AUTHORSHIP

Prepared by:

[Project Leader]

# AUTHORIZATION

Approved:

Date:

Date:

[System Analyst]

Date:

[Project Leader]

Date:

[Project Manager]